## Slide 1: Platform Observability Assessment Kick-Off
Aug 2026

## Slide 2: Agenda
01 What We Know Right Now
02 Problem Statement
03 Scope Definition
04 Expected Outcomes
05 Assessment Plan and Approach
06 RAID — Risks, Assumptions, Dependencies

## Slide 3: What We Know Right Now
01

## Slide 4: Platform Overview
Component | Role / Function | Status
CDN | Edge layer — ingress, caching, DDoS protection | Provider TBC
Apache | Web / reverse proxy tier | Active
Azure VMs | Legacy application components | Migration → AKS in progress
Azure Kubernetes Service | Modernised microservices, namespace-based env isolation | Active
Azure SQL Database | Managed relational DB with HA | Active
Azure Service Bus | Regional async messaging between services | Active
App Gateway + WAF | L7 load balancing and web application firewall | Active
12 production environments (primary + DR) across US, UK, AU | DE in progress, CA planned | Monitoring: Azure Monitor + Datadog single tenant

## Slide 5: Current Monitoring State
What is in place
• Azure Monitor + Log Analytics for infrastructure signals
• Datadog as primary monitoring platform (migrated from Splunk ~2 yrs ago)
• Single Datadog tenant covers ALL consumer environments
• Tag-based environment isolation: env / consumer / service
• AKS namespace-based environment separation
What we do not know yet
• Which tiers have no monitoring coverage (dark)
• Whether all 12 environments are consistently configured
• Actual alert coverage vs. real failure modes
• Whether SLA obligations map to any observable signal
• APM instrumentation depth and trace coverage
• Incident history and MTTD / MTTR baseline
• Whether tag governance is enforced or ad hoc

## Slide 6: Problem Statement
02

## Slide 7: Problem Statement
Current State
Observability is reactive. Consumers report failures before internal monitoring detects them.
Confirmed evidence:
• Database crash caused consumer-facing outage — detected externally
Root causes (hypothesised — to validate):
• Instrumentation gaps — tiers emit insufficient signals
• Alert coverage gaps — critical failure modes not monitored
• Alert quality — noisy, mis-tuned, or misrouted
• SLA/SLO disconnect — no automated observability backing
• Governance gaps — no enforced monitoring standard
Target State — North Star
• Platform health continuously and proactively monitored across all tiers and all consumer environments
• Every SLA obligation backed by an automated signal that alerts before breach occurs
• Incidents detected internally — MTTD in minutes, not hours reported by consumers
• Engineering, operations, and leadership each have purpose-built visibility
• Observability standards governed, owned, and consistently applied across all teams

## Slide 8: Scope Definition
03

## Slide 9: In-Scope Activities — Phase 1
# | Activity | What We Are Assessing
1 | Application & Infrastructure Landscape Review | Identify all in-scope tiers, services, components — the factual baseline
2 | Observability Coverage Evaluation | Log pipelines, metrics, tracing — identify dark tiers and instrumentation blind spots
3 | Alerting & Detection Gap Analysis | Alert inventory vs. Critical/High failure modes; gaps where consumers detect before monitoring
4 | APM Review | Evaluate whether APM depth supports effective root cause analysis
5 | SLA / SLO Observability Review | Map SLA commitments to SLO monitors; identify gaps where obligations lack observable signals
6 | Dashboard & Visibility Assessment | Evaluate dashboards against audience needs: engineering, operations, leadership
7 | Operational Processes Review | Incident workflow: routing, on-call, runbooks, escalation paths, MTTD / MTTR posture
8 | Governance Model Review | Current-state governance: tagging, ownership, access control, standards consistency

## Slide 10: Scope Boundaries and Constraints
In Scope
Platform tiers:
• CDN / Apache / AKS / Azure VMs
• Azure SQL, Service Bus, Blob, App Gateway + WAF
• Datadog — monitors, APM, logs, SLOs
• Azure Monitor + Log Analytics
Active regions:
• US, UK, AU (DE — to confirm today)
Capacity:
• 2 specialists | 4 weeks of active delivery
Out of Scope — Phase 2
• Multi-region consistency deep-dive
• Datadog platform utilisation optimisation
• Monitoring-as-code / CI/CD automation
• Business activity monitoring — consumer KPIs
• Unified observability architecture implementation
• Standardisation at scale / migration execution
* Week 1 is a landscape discovery phase — if undisclosed components surface, both parties agree in writing whether to include them or defer to Phase 2.

## Slide 11: Expected Outcomes
04

## Slide 12: Expected Outcomes and Deliverables
# | Deliverable | Primary Audience
1 | Technical Assessment Report | Engineering & Architecture
2 | Target Observability Architecture | Engineering & Architecture
3 | Improvement Roadmap | Engineering & Leadership
4 | Governance Guidelines | Engineering & Operations
5 | Executive Summary | Leadership & Stakeholders
Technical gaps identified
• Dark tiers with no monitoring coverage
• Missing or misconfigured alert rules
• SLA obligations without observable signals
• APM instrumentation and trace coverage gaps
Process and governance gaps identified
• Ownership and governance model gaps
• Runbook quality and on-call effectiveness
• Absence of SLO-driven alerting practice
• Quick wins for immediate improvement

## Slide 13: Assessment Plan
05

## Slide 14: 4-Week Assessment Plan
Week | Focus | Key Activities
Week 1 | Discovery & Landscape | Kick-off · Engineering Workshop · Access provisioning · Platform landscape mapping · Initial evidence collection
Week 2 | Technical Analysis | Operations Workshop · Datadog deep-dive (monitors, APM, logs, SLOs) · Azure Monitor review · AKS / source code / CI/CD review
Week 3 | Gap Analysis | Structured gap analysis across all domains · Findings drafting · Interim Findings Review with Client
Week 4 | Recommendations & Delivery | Target architecture · Roadmap · Report finalisation · Leadership Workshop (conditional) · Final Presentation
* Timeline is indicative. Client-side delays in Weeks 1–2 will be flagged by end of Week 2 with an updated delivery date.

## Slide 15: Workshops and Toolset
Workshop | Timing
Kick-off | Week 1
Engineering Workshop | Week 1
Operations / On-call Workshop | Week 2
Interim Findings Review | Week 3
Leadership Workshop (conditional) | Wk 3–4
Final Delivery Presentation | Week 4
Toolset
Azure CLI + Portal
Diagnostic settings, Azure Monitor, Log Analytics, AKS
Datadog API (read-only)
Programmatic export of monitors, dashboards, SLOs, APM, log indexes
Datadog UI — Viewer role
Direct inspection and screenshot evidence
Source code + CI/CD (read-only)
Instrumentation verification; observability-as-code assessment
Claude — Anthropic AI
Evidence analysis, gap identification, report drafting — client confirmation required

## Slide 16: RAID — Risks, Assumptions, Dependencies
06

## Slide 17: Risks
# | Risk | Impact | Owner
R1 | Azure / Datadog access not provisioned by Week 1 Day 1 | Timeline compresses or slips entirely | Client
R2 | Key workshop participants unavailable or substituted with proxies | Findings based on assumptions; reduced accuracy | Client
R3 | SLA/SLO definitions, architecture docs, or incident records unavailable | Gap analysis lacks contractual grounding; findings understate severity | Client
R4 | Platform scope larger than known — services discovered in Week 1 | Gaps in unknown components go unassessed | Both
R5 | IAM / security policies block required read-only access | Domain coverage reduced; findings may be caveated | Client
R6 | Single Datadog tenant complexity makes per-environment analysis difficult | Environment-specific gaps may go undetected | Both
R7 | AI tooling not cleared by Client data handling policy | Methodology revised mid-delivery; timeline extends | Both
R8 | Delays in Weeks 1–2 compress analysis and delivery weeks | Report and architecture quality reduced | Both

## Slide 18: Assumptions and Dependencies
Dependency | Blocking? | Required by
Azure read-only access (Reader, Log Analytics, AKS Cluster User, Policy Reader) | BLOCKING | Week 1, Day 1
Datadog API Key + Application Key (read-only) | BLOCKING | Week 1, Day 1
Datadog Viewer role (UI access) | BLOCKING | Week 1, Day 1
Source code repository read access | BLOCKING | Week 1
In-scope subscription IDs list | BLOCKING | Kick-off
AI tooling acceptable-use confirmation | BLOCKING | Before Week 1
Named Engineering Workshop participants | BLOCKING | Before Week 1 ends
Named Operations Workshop participants | BLOCKING | Before Week 2
SLA/SLO definitions + incident post-mortems | Required | Week 2

## Slide 19: Next Steps — To Close in This Session
Actions required before Week 1 begins:
• Client confirms or adjusts platform scope — tiers, regions, environments
• Client confirms AI tooling acceptable-use policy
• Client nominates named participants for Engineering and Operations workshops
• Client names a single point of contact for access provisioning
• Client provides list of in-scope Azure subscription IDs
• Both parties agree access provisioning deadline — target: 2 business days post kick-off
• Both parties confirm date and time for Week 1 Engineering Workshop
• Client confirms documentation owner for SLA/SLO definitions and incident records

## Slide 20: Thank You